Beauty Black Friday Live - Post-Campaign Review

Results vs Targets

| Metric | Target (see the campaign plan) | Actual | Verdict |
| --- | --- | --- | --- |
| GMV | $500K-$700K | $600.4K | On target |
| Conversion rate | 6%-8% | 8.62% | Above target |
| Peak concurrent viewers | 5,000-7,000 | 6,488 | On target |
| Operating cost | Planned $71.1K | Actual $73.6K | 3.5% over budget; ad bids rose during Black Friday, the risk the plan flagged |

ROI (the formula changed; here is why)

The first two versions were wrong. The first one subtracted only the operating cost, not the product cost, so ROI looked too high. The second one added the product cost to the denominator, which is also wrong: product cost is already deducted in campaign_products.profit (profit = sales - product cost; the customer pays for the goods, it is not money the company spent on this campaign). The real question is: how much profit did the marketing spend (the operating cost) bring in?

- Total product profit (sum of profit over the 3 featured products in campaign_products, product cost already deducted): $168.8K

- Actual operating cost (campaigns.actual_operating_cost): $73.6K

- ROI = total product profit / operating cost = 168.8 / 73.6 ≈ 2.29: every $1 of marketing spend brought back about $2.29 of product profit

Both numbers now come from structured fields (SUM(campaign_products.profit) and campaigns.actual_operating_cost), so the review no longer estimates them by hand or improvises a formula.

Product Breakdown

| Product | Units sold | Sales | Profit | Margin | Return rate |
| --- | --- | --- | --- | --- | --- |
| Sheet Mask | 470 | $131.6K | $45.4K | 34.52% | 10.2% |
| Lipstick | 528 | $127.6K | $59.2K | 46.36% | 19.2% |
| Serum | 796 | $110.1K | $64.2K | 58.26% | 19.7% |

Findings:

- Serum had the highest margin (58.26%), the most units and the most profit. The plan positioned it as the traffic driver; it turned out to be the most profitable product as well. A winter skincare staple does not need a deep discount to sell.

- Sheet masks had the highest sales but the lowest margin (34.52%). The "20% off two boxes" bundle drove volume and gave away most of the margin.

- Lipstick and serum came back at almost twice the return rate of sheet masks (about 19% vs 10%). For lipstick this is probably shade mismatch; worth checking the return reasons before the next campaign.

- Operating cost was 3.5% over budget, the overrun the plan warned about ("ad placement bids usually rise during Black Friday"). It was small this time, but it points the same way as other seasonal campaigns.

Recommendations for Similar Campaigns

- Budget seasonal campaigns with a buffer based on the past overrun of actual over planned cost, instead of the ratio used for regular campaigns

- Keep serum as the hero product, and test a smaller bundle discount on sheet masks to win back margin

- Look into lipstick returns (shade guidance during the stream, swatch close-ups) before featuring it again